## Sheet1
Risk ID | Risk Description | Affected Asset | Likelihood | Impact | Risk Score | Mitigation Strategy
R-001 | Phishing email targeting library staff | Staff PCs | High | Medium | 12 | Conduct phishing awareness training; enable MFA
R-002 | Ransomware attack on patron database | Patron Database Server | Medium | High | 15 | Implement backups; restrict admin access; antivirus
R-003 | Unauthorized access to payroll data | HR Payroll System | Low | High | 10 | Use strong RBAC; enable audit logs; secure credentials
R-004 | Router misconfiguration exposing Wi-Fi | Public Wi-Fi Router | Medium | Medium | 9 | Regular firmware updates; change default credentials
R-005 | Vendor CMS breach leaking event data | Website CMS | Medium | Medium | 9 | Review vendor SLA; sanitize data; use web firewall
R-006 | Unpatched kiosk software vulnerability | RFID Checkout Kiosks | High | Low | 8 | Patch regularly; restrict USB access
R-007 | Failed backup leading to data loss | Backup Storage Device | Low | High | 10 | Test backups monthly; use off-site replication